International School

Capstone Project 2

CMU SE - 450_C2SE.13

Project Plan Document

Version 1.0

Date: March 13th, 2025

CalAI – Calorie & Nutrition Tracker

Submitted by C2SE.13

Dat, Nguyen Tan                 27211202495

Nhi, Nguyen Thi Dung    	  28209054723

Khanh,Truong bao 	  28211101470

Toan, Pham Le Duc	  28211101330

Huy, Nguyen Ho Khai	  28219047115

Approved by

MSc. Nguyen Manh Duc

Review Panel Representative:

Name

Signature

Date

Capstone Project 2

Name

Signature

Date

| DOCUMENT INFORMATION |  |  |  |
| --- | --- | --- | --- |
| Document Title | Project Plan Document |  |  |
| Author(s) | Nguyen Tan Dat |  |  |
| Role | Product Owner, Team Member, Scrum Master |  |  |
| Date | 18 Feb 2025 | File name | C2SE13_ProjectPlan_CNT_ver1.0.docx |
| URL |  |  |  |
| Access | Project and CMU Program |  |  |

REVISION HISTORY

| Version | Person(s) | Date | Description |
| --- | --- | --- | --- |
| 1.0 | All Members | 13 March 2026 | Create a Project Plan document |
| 1.1 | All Members | 01 May 2026 | Update Cost |

TABLE OF CONTENTS

1.	Introduction	7

1.1. Purpose	7

1.2. Project Overview	7

1.3. Project Deliverable	7

2.	Team Organization	8

2.1.	Scrum Team Information	8

2.2.	Role and Responsibility	8

2.3.	Communication Methodology	10

2.4.	Communication Methodology	10

3.	Development Process	12

4.	Schedule and Cost	13

4.1.	Detailed Schedule	13

4.2.	Cost	17

4.2.1.	Cost Person/Hours	17

4.2.2.	Total Cost Estimate	17

5.	Project Risk	18

6.	Deliverables	21

LIST OF TABLE

Table 1: Scrum Team Organization	8

Table 2: Role and Responsibilities	8

Table 3: Communication Methodology	10

Table 4: Communication and Report	10

Table 5: Detailed Schedule	13

Table 6: Cost person/hours	17

Table 7: Total cost estimation	17

Table 8: Description Cost	18

Table 9: Rating for likelihood and seriousness of each risk	18

Table 10: Project Risk	18

Table 11: Deliverables	21

LIST OF FIGURE

Figure 1: Communication and Report	12

- Introduction

## 1.1. Purpose

This document provides a summary of the project objectives, work breakdown, milestones, required resources, overall schedule, and budget allocation for the CalAI – Calorie & Nutrition Tracker project. The primary purpose is to ensure the project is completed on time, meets all technical requirements, and adheres to the plan outlined in the proposal.

## 1.2. Project Overview

The project aims to develop CalAI – an advanced AI-based system that helps users achieve their personal health and fitness goals through dietary management. The system addresses current challenges in accurately tracking calorie intake and understanding the nutritional composition of diverse food sources. CalAI is not just a conventional record-keeping tool, but a Global Culinary Intelligence Platform with key features: Utilizing an Agentic Retrieval-Augmented Generation (RAG) system for in-depth analysis and personalized guidance across diverse cuisines worldwide.Automatically identifying food from images using machine learning models (CNN or Vision Transformer). Providing customized meal plans based on user profiles, health status, and historical dietary goals.And integrating an AI chatbot for 24/7 support, providing dietary guidance and answering user questions.

## 1.3. Project Deliverable

The project will be implemented for users such as system administrator, system users.

# Team Organization

## Scrum Team Information

Table 1: Scrum Team Organization

| Full Name | Email | Phone | Position |
| --- | --- | --- | --- |
| MSc.Nguyen Manh Duc | trannhatvinh@dtu.edu.vn | 0918577644 | Mentor |
| Dat, Nguyen Tan | Nguyentandat090904@gmail.com | 0904073917 | Scrum Master and Dev-team |
| Nhi, Nguyen Thi Dung | dungnhi077@gmail.com | 0848091212 | Product Owner and Dev-team |
| Khanh,Truong bao | truongkhanh13572468@ gmail.com | 0795781375 | Dev-team |
| Toan, Pham Le Duc | phamlductoan@gmail.com | 0365000847 | Dev-team |
| Huy, Nguyen Ho Khai | huy312160@gmail.com | 0935418951 | Dev-team |

## Role and Responsibility

Table 2: Role and Responsibilities

| Role | Responsibility | Name/Title |
| --- | --- | --- |
| Product Owner | Understand the user and customers with their needs. Collaborate with the development team. Manage the stakeholders. Describe the user experience and product features. Provides detailed user stories. | Dat, Nguyen Tan |
| Scrum Master | Communicate the value of Scrum. Teach the organization on Scrum to maximize business value. Attend all Scrum meetings Preserve the integrity and spirit of the Scrum framework. Maintain the focus of the Team. Make the Team aware of impediments and facilitate efforts to resolve them. Serve as a coach and mentor to members of the Team. Respectfully hold the Team, Product Owner, and Stakeholders accountable for their commitments. Continually work with the Team and business to find and implement improvements. | Dat, Nguyen Tan |
| Secretary | Record the content of group meetings and activities of the member. | Dat, Nguyen Tan |
| Reviewer | Review documents. | All Members |
| Developer | Analysis of the functions and requirements of the product. Code and test. Fix error. | All Members |
| Analyzer | Gather user stories. Analysis of user story to specify Document. | All Members |
| Tester | Do the Test plan. Creation of test designs, test processes, test cases, and test data. Carry out testing as per the defined procedures. Graph the results and make sure people know when test results decline. Prepare all reports related to software testing carried out. Analysis and evaluate the Test result. Ensure that all tested-related work is carried out as per the defined standards and procedures. | All Members |
| Mentor | Guide on the process. Monitoring all activities of the Team. Help with anything. | Duc, Nguyen Manh |

## Communication Methodology

Table 3: Communication Methodology

| Audience/ Attendees | Topic/ Deliverable | Frequency | Method |
| --- | --- | --- | --- |
| Mentor and Team member | Project Progress Review | Weekly | Meeting, Email, Zalo |
| Team Member | Project Progress Review and Daily Meeting | Daily | Trello, GitHub, Google Meet |

## Communication Methodology

Table 4: Communication and Report

| Type of communication | Methods, tools | Frequency | Information | People |
| --- | --- | --- | --- | --- |
| Communication among group |  |  |  |  |
| Scrum meeting | Face-to-face or Hangouts | Every two day | Informed about what was done in the last 24 hours, working on plans for today, the difficulties encountered and the solutions required, just meeting 10-15 minutes. | Project team |
| Sprint Planning Meeting | Meet face to face | 15-20 days | All members of the team together to analyze the requirements and functions, work on the sprint going to do, planning and design for the sprint. | Project team |
| Retrospective meeting | Meet face to face | 15-20 days | Complete documentation. For each stage, sharing materials, given the strengths and weaknesses of each. Period for each member and the solution calculated measurement project. | Project team and Mentor |
| Demo | Meeting online | Every day | A web-based task tracking system. To manage or divide tasks, and report bugs/issues. | Project team. |

# Development Process

Figure 1: Communication and Report

- Scrum is an iterative and incremental agile software development framework for managing software projects and product or application development.

- Scrum focuses on project management institutions where it is difficult to plan.

- Mechanisms of empirical process control, where feedback loops that constitute the core management technique are used as opposed to traditional command-and-control management.

- Its approach to planning and managing projects is by bringing decision-making authority to the level of operation properties and certainties.

The benefit of the methodology:

− The project can respond easily to change.

− Problems are identified early.

− Customers get the most beneficial work first.

− Work done will better meet the customer’s needs.

− Improved productivity.

− Ability to maintain a predictable delivery schedule.

# Schedule and Cost

## Detailed Schedule

Table 5: Detailed Schedule

| No. | Task Name | Start | Finish | Effort |
| --- | --- | --- | --- | --- |
| 1 | Initial | 03/09 | 10/09 | 24 hrs |
| 1.1 | Gathering Requirement | 03/09 | 05/09 | 8 hrs |
| 1.1.1 | Get requirement from Mentor MSc.Nguyen Manh Duc | 09/02 | 09/02 | 2 hrs |
| 1.1.2 | Analyzing requirement | 10/02 | 11/02 | 6 hrs |
| 1.2 | Create Proposal Document | 03/02 | 10/02 | 16 hrs |
| 1.2.1 | Product Definition | 02/02 | 03/02 | 3 hrs |
| 1.2.2 | Business Need | 04/02 | 05/02 | 2 hrs |
| 1.2.3 | Prior Art | 06/02 | 07/02 | 3 hrs |
| 1.2.4 | Proposed Solution | 08/02 | 09/02 | 3 hrs |
| 1.2.5 | Master Plan | 10/02 | 10/02 | 5 hrs |
| 2 | Start Up | 14/02 | 20/02 | 46 hrs |
| 2.1 | Project kick-off | 14/02 | 14/02 | 2 hrs |
| 2.2 | Create Document | 15/02 | 20/02 | 46 hrs |
| 2.2.1 | Project’s Meeting | 15/02 | 15/02 | 3 hrs |
| 2.2.2 | Create User Stories | 15/02 | 15/02 | 6 hrs |
| 2.2.3 | Create Product Backlog | 16/02 | 16/02 | 10 hrs |
| 2.2.4 | Review Document | 17/02 | 17/02 | 5 hrs |
| 2.2.5 | Create Project Plan | 18/02 | 18/02 | 10 hrs |
| No. | Task Name | Start | Finish | Effort |
| 2.2.6 | Create Architecture Design Document | 19/02 | 19/02 | 10 hrs |
| 2.2.7 | Review Document | 20/02 | 20/02 | 2 hrs |
| 3 | Development | 21/02 | 23/05 | 1032 hrs |
| 3.1 | Sprint 1 | 21/02 | 18/03 | 365 hrs |
| 3.1.1 | Register an Account | 21/02 | 26/02 | 30hrs |
| 3.1.2 | Login | 21/02 | 23/02 | 20 hrs |
| 3.1.3 | Logout | 22/02 | 22/02 | 8 hrs |
| 3.1.4 | Forgot password | 26/02 | 27/02 | 17 hrs |
| 3.1.5 | Reset Password | 27/02 | 27/02 | 10 hrs |
| 3.1.6 | OTP Verification (Register) | 23/02 | 23/02 | 10 hrs |
| 3.1.7 | OTP Verification (Forgot Password) | 26/02 | 26/02 | 10 hrs |
| 3.1.8 | Onboarding Setup | 28/02 | 04/03 | 40 hrs |
| 3.1.9 | Create User Profile | 05/03 | 06/03 | 20 hrs |
| 3.1.10 | Update Personal Information | 06/03 | 06/03 | 10 hrs |
| 3.1.11 | Set Personal Diet Goals | 07/03 | 07/03 | 15 hrs |
| 3.1.12 | Calculate Daily Calorie Target | 10/03 | 11/03 | 20 hrs |
| 3.1.13 | View Dashboard Overview | 11/03 | 11/03 | 10 hrs |
| 3.1.14 | View Daily Nutrition Summary | 12/03 | 12/03 | 15 hrs |
| 3.1.15 | Add Meal Record Manually | 13/03 | 13/03 | 20 hrs |
| 3.1.16 | Edit Meal Record | 13/03 | 13/03 | 10 hrs |
| 3.1.17 | Delete Meal Record | 14/03 | 14/03 | 15 hrs |
| 3.1.18 | Search Food Items from Database | 14/03 | 14/03 | 20 hrs |
| 3.1.19 | Select Serving Size and Portion | 17/03 | 17/03 | 10 hrs |
| 3.1.20 | View Food Nutrition Details | 17/03 | 17/03 | 20 hrs |
| 3.1.21 | View Meal History | 18/03 | 18/03 | 20 hrs |
| 3.1.22 | Basic User Settings | 18/03 | 18/03 | 15 hrs |
| 3.2 | Sprint 2 | 19/03 | 11/04 | 216 hrs |
| 3.2.1 | Upload Food Image | 19/03 | 20/03 | 10 hrs |
| 3.2.2 | Capture Food Image from Camera | 19/03 | 20/03 | 10 hrs |
| 3.2.3 | Validate Food Image Input | 21/03 | 22/03 | 10 hrs |
| 3.2.4 | Preprocess Food Image | 21/03 | 22/03 | 10 hrs |
| 3.2.5 | Detect Dish from Image | 24/03 | 25/03 | 10 hrs |
| 3.2.6 | Identify Food Items | 24/03 | 25/03 | 10 hrs |
| 3.2.7 | Estimate Portion Size | 26/03 | 26/03 | 8 hrs |
| 3.2.8 | Calculate Estimated Calories | 26/03 | 26/03 | 8 hrs |
| 3.2.9 | Generate Nutrition Breakdown | 27/03 | 28/03 | 10 hrs |
| 3.2.10 | Display Food Analysis Result | 27/03 | 28/03 | 10 hrs |
| 3.2.11 | Confirm or Edit Analysis Result | 29/03 | 29/03 | 8 hrs |
| 3.2.12 | Save Food Analysis to Meal Log | 29/03 | 29/03 | 8 hrs |
| 3.2.13 | Update Daily Calorie Intake | 30/03 | 30/03 | 8 hrs |
| 3.2.14 | Update Daily Nutrition Summary | 31/03 | 01/04 | 10 hrs |
| 3.2.15 | Show Goal Progress After Meal Logging | 31/03 | 01/04 | 10 hrs |
| 3.2.16 | View Meal Details from Analysis Result | 02/04 | 03/04 | 15 hrs |
| 3.2.17 | Reanalyze Food Image | 04/04 | 04/04 | 8 hrs |
| 3.2.18 | Delete Logged Analysis Result | 04/04 | 04/04 | 8 hrs |
| 3.2.19 | View Analysis History | 05/04 | 10/04 | 30 hrs |
| 3.2.20 | Handle Low-Confidence Recognition Result | 11/04 | 13/04 | 15 hrs |
| 3.3 | Sprint 3 | 12/04 | 02/05 | 236 hrs |
| 3.3.1 | Chat with AI Nutrition Assistant | 12/04 | 12/04 | 8 hrs |
| 3.3.2 | Understand User Nutrition Query | 13/04 | 14/04 | 18 hrs |
| 3.3.3 | Retrieve Nutrition Knowledge from RAG System | 14/04 | 15/04 | 20 hrs |
| 3.3.4 | Generate AI Nutrition Response | 15/04 | 17/04 | 25 hrs |
| 3.3.5 | Answer Questions about Calories and Nutrients | 17/04 | 19/04 | 25 hrs |
| 3.3.6 | Provide Personalized Diet Recommendations | 19/04 | 21/04 | 25 hrs |
| 3.3.7 | Suggest Meal Plans Based on User Goals | 21/04 | 23/04 | 30 hrs |
| 3.3.8 | Suggest Healthier Food Alternatives | 23/04 | 25/04 | 25 hrs |
| 3.3.9 | Summarize Daily Nutrition Intake | 25/04 | 26/04 | 15 hrs |
| 3.3.10 | Provide Goal-Based Progress Advice | 26/04 | 28/04 | 15 hrs |
| 3.3.11 | View AI Chat History | 28/04 | 02/05 | 30 hrs |
| 3.4 | Sprint 4 | 03/05 | 23/05 | 215 hrs |
| 3.4.1 | Send Meal Reminder Notifications | 03/05 | 04/05 | 20 hrs |
| 3.4.2 | Send Hydration Reminder Notifications | 05/05 | 06/05 | 20 hrs |
| 3.4.3 | Send Daily Nutrition Summary Alerts | 07/05 | 08/05 | 15 hrs |
| 3.4.4 | Send Goal Achievement Notifications | 09/05 | 10/05 | 15 hrs |
| 3.4.5 | Schedule Notification Jobs | 11/05 | 12/05 | 15 hrs |
| 3.4.6 | View User Progress Analytics | 13/05 | 14/05 | 20 hrs |
| 3.4.7 | View Nutrition Dashboard Statistics | 15/05 | 16/05 | 20 hrs |
| 3.4.8 | Manage User Accounts | 17/05 | 18/05 | 12 hrs |
| 3.4.9 | Configure Access Rights | 19/05 | 22/05 | 60 hrs |
| 3.4.10 | Manage Food and Nutrition Data | 23/05 | 23/05 | 10 hrs |
| 3.4.11 | Monitor System Performance | 24/05 | 24/05 | 8 hrs |
| 4 | Project’s Retrospective Meeting | 24/05 | 24/05 | 9 hrs |
| 4.1 | Project’s Retrospective Meeting | 25/05 | 25/05 | 9 hrs |
| 5 | Final Release | 26/05 | 26/05 | 8 hrs |
| 5.1 | Final Release | 27/05 | 27/05 | 8 hrs |

## Cost

### Cost Person/Hours

Table 6: Cost person/hours

| Full Name | Role | Salary Rate (USD/hour) |
| --- | --- | --- |
| Dat, Nguyen Tan | Scrum Master | $2 |
| Nhi, Nguyen Thi Dung | Product Owner | $2 |
| Khanh,Truong bao | Team Member | $2 |
| Toan, Pham Le Duc | Team Member | $2 |
| Huy, Nguyen Ho Khai | Team Member | $2 |

### Total Cost Estimate

Table 7: Total cost estimation

| No. | Criteria | Price | Total (USD) |
| --- | --- | --- | --- |
| 1 | Working cost | $2/hours | $4160 |
| 2 | Deployment cost | $20/month | $60 |
| 3 | Contingency cost | $422 | $422 |
|  | Total cost |  | $4642 |

Table 8: Description Cost

| Description | Amount | Unit |
| --- | --- | --- |
| Number of Members | 5 | Person |
| Number of working hours per day | 4 | Hours |
| The cost of working per hour per member | 2 | USD |
| The duration of the project | 3 | Month |
| The number of working days | 104 | Days |

The explanation for the table:

- Amount of working cost = 5 members * 4 hours * 2 USD * 104 days

- Deployment cost = 20 USD * 3 month

- Contingency cost = 10% * (amount of working cost + deployment cost)

# Project Risk

Table 9: Rating for likelihood and seriousness of each risk

| RATING FOR LIKELIHOOD AND SERIOUSNESS OF EACH RISK |  |  |  |
| --- | --- | --- | --- |
| L | Rated as Low | E | Rated as Extreme (Used for Seriousness only) |
| M | Rated as Medium | NA | Not Assessed |
| H | Rated as High |  |  |

Table 10: Project Risk

| Risk | Definition | Level | Likelihood | Mitigation Strategy |
| --- | --- | --- | --- | --- |
| Estimates of project planning | The plan may be delayed for the initial estimate of the project. | L | L | Analysis and assessment of the scale. Reduce requirements. |
| Requirements | Internal contradictions that may exist in the request. Important requirements may be missing from the formal requirements specification. Requirements may change during project execution. | H | H | Uniform requirements before analysis. |
| Estimated project schedule | Time sort of work. | E | E | A time project was created to be updated and evaluated regularly. |
| Programming experience | Programming Languages and Technology | M | L | Experience sharing is used to reduce the research time. |
| Technical processes | The tea procedure cannot meet the requirements of specific solutions. A new process may be required. The process can be improved and more efficient. | L | M | Analysis of requirements and processes to ensure appropriate levels. If the new process is needed, we need to evaluate whether this response has improved over the old process. |
| Network | Block by Limited Bandwidth | H | H | Upgrade transmission line network |
| Time | The project implementation period is too short, so our team cannot complete this project in a short time. During project implementation, our team learned and had more work to do, but our team could not focus all their time on carrying out this project. | H | M | Reduce time and increase individual personal time working during their stay on the 7th day and Sunday. |

| Project Management | The project management system may not be sufficient to support the requirements of the project. | L | H | Discuss with the group to offer solutions and consistent accuracy. |
| --- | --- | --- | --- | --- |

# Deliverables

Table 11: Deliverables

| No. | Document | Deadline | File Name |
| --- | --- | --- | --- |
| 1 | Proposal Document | 27 May 2025 | C2SE13_Proposal_CNT_ver1.0.docx |
| 2 | Product Backlog Document | 27 May 2025 | C2SE13_ProductBacklog_CNT_ver1.0.docx |