## Main
Scrum Project
Product | CalAI – Calorie & Nutrition Tracker
Active versions
Team |  |  | Product Owner
Scrum Master | Nguyễn Tấn Đạt |  | Other Stakeholders
Developers | Phạm Lê Đức Toàn
Nguyễn Hồ Khải Huy
Nguyễn Thị Dung Nhi
Trương Bảo Khanh
Projects | [5 empty] | Sprint Plan |  | Project #1
Id | Description | Start | End | Status | Remarks | Sprint | Start | End | Status | Work planned (Committed) | Work spent (Delivered) | Remarks
1 | Initial release | 2019-01-07 | 2019-03-15 | In Progress |  | 1 | 2019-01-07 | 2019-01-18 | Complete | 3
[6 empty] | 2 | 2019-01-21 | 2019-02-01 | Complete | 25
[6 empty] | 3 | 2019-02-04 | 2019-02-15 | Complete | 20
[6 empty] | 4 | 2019-02-18 | 2019-03-01 | Complete | 25
[6 empty] | 5 | 2019-03-04 | 2019-03-15 | In Progress | 20
Formulas:
Project #1 = [Start]+11
Start = [Project #1, row above]+3

## Product Backlog
Product Backlog
Id | Heading | As a.. | I want to .. | so that .. | Acceptance Criteria | Remarks | Priority | Status | Type | Project Id | Sprint No | Estimate (Hours) | Effort (Actual) | Owner | Status | Remarks
PB01 | Register an Account | User | Create an account | I can access personalized nutrition tracking services. | - User enters required information; system validates input - The system sends OTP/email verification. - Account is activated after successful verification |  | 1 |  |  |  | 1 | 30
PB02 | Login | User/Admin | Login to website | I can access my dashboard and personal data securely. | -Valid credentials allow login. -Invalid credentials show an error. -Authenticated users are redirected to the dashboard. |  | 1 |  |  |  | 1 | 35
PB03 | Log out | User | Log out of the system | My account remains secure after use | -User can log out from the interface -Current session is terminated -Protected pages require login again. |  | 2 |  |  |  | 1 | 25
PB04 | Forgot password | User | Request password recovery | I can regain access to my account when I forget my password. | -User submits registered email. -System sends recovery OTP/link. -System informs user if the request is successful. |  | 2 |  |  |  | 1 | 30
PB05 | Reset Password | User | Reset my password securely | I can continue using the platform safely. | -User verifies OTP/token. -The new password must satisfy security rules. -The password is reset successfully. -The user can log in with the new password. |  | 1 |  |  |  | 1 | 30
PB06 | Manage User Profile | User | Create and update my personal profile | The system can provide more personalized nutrition recommendations. | -User can view profile. -User can edit personal information. -Updated profile is saved successfully. |  | 1 |  |  |  | 1 | 30
PB07 | Set Personal Diet Goals | User | Define my calorie and nutrition goals | I can track progress based on my health objectives. | -User can input goals. -System stores goals. -Goals are shown on dashboard and progress views |  | 1 |  |  |  | 1 | 40
PB08 | View Dashboard Overview | User | View my dashboard | I can monitor my meals, calories, and nutrition progress in one place. | -Dashboard displays daily summary -Dashboard reflects logged meals -Progress is shown against user goals. |  | 1 |  |  |  | 1 | 40
PB09 | Log Meals Manually | User | Add and manage meal records manually | I can track my food intake even without image analysis | -User can add meal entries. -User can edit/delete entries. -Entries update nutrition summary. |  | 1 |  |  |  | 1 | 30
PB10 | Search Food and Nutrition Data | User | Search food items and nutrition details | I can record meals accurately and make informed diet choices. | -User can search food database. -System returns matching food items. -Nutrition details are displayed. |  | 3 |  |  |  | 1 | 40
PB11 | View Meal History | User | Review my logged meals. | I can monitor my past eating habits and progress over time. | -User can view past meals -Meals are ordered by date/time -History supports detailed viewing. |  | 1 |  |  |  | 1 | 50
PB12 | Upload and Recognize Food Image | User | Upload or capture a food image and let the system recognize the food items. | I can analyze my meal quickly and accurately | -User can upload or capture a food image -System validates and processes the image -System identifies the food items from the image -Recognized results are displayed to the user -User can continue to portion estimation and nutrition analysis |  | 1 |  |  |  | 2 | 50
PB13 | Estimate Portion Size | User | Have the system estimate food portions | I can receive more accurate calorie and nutrition calculations. | -System estimates portion size from image. -Estimated portion is shown to user. -User can confirm or adjust it. |  | 2 |  |  |  | 2 | 40
PB14 | Calculate Calories and Nutrition | User | Receive calorie and nutrient analysis for meals | I can better understand the nutritional value of what I eat | -System calculates calories and nutrients. -Result includes nutrition breakdown. -Result is presented clearly. |  | 2 |  |  |  | 2 | 50
PB15 | Save Food Analysis Results | User | Save analyzed food results to my meal log | My nutrition tracking remains complete and consistent. | -Analyzed result can be saved. -Saved result updates dashboard and summary. -Saved record appears in meal history. |  | 2 |  |  |  | 2 | 30
PB16 | Handle Low-Confidence Recognition | User | Review and correct uncertain | I can improve the accuracy of my meal records. | -System flags low-confidence results. -User can edit recognized items. -Corrected result can be saved. |  | 3 |  |  |  | 2 | 30
PB17 | Chat with AI Nutrition Assistant | User | Ask nutrition-related questions | I can receive quick guidance and support for my diet decisions. | -User can submit questions. -AI returns relevant responses. -Conversation is shown in chat format. |  | 2 |  |  |  | 3 | 40
PB18 | Receive Personalized Diet Recommendations | User | Get AI-based recommendations and meal suggestions | I can follow a diet plan suited to my goals and preferences. | -Recommendations are based on user profile/goals. -Suggestions are relevant to nutrition context. -Recommendations are displayed clearly. |  | 4 |  |  |  | 3 | 30
PB19 | Generate Meal Plans | User | Receive suggested meal plans | I can manage my daily nutrition more effectively. | -System generates meal plan suggestions. -Plan aligns with goals/preferences. -User can view recommended meals. |  | 2 |  |  |  | 3 | 50
PB20 | View AI Chat History | User | Review previous conversations with the AI assistant | I can revisit useful nutrition advice when needed. | -User can access past chats. -Chat history is stored and displayed. -User can reopen previous conversations. |  | 3 |  |  |  | 3 | 40
PB21 | Receive Meal Reminder Notifications | User | Receive reminders for meals | I can maintain healthy eating habits consistently. | -System sends scheduled reminders. -Reminders are relevant to user schedule/goals. -User can receive notification messages. |  | 2 |  |  |  | 4 | 20
PB22 | Receive Nutrition Summary Alerts | User | Receive daily nutrition summaries and progress alerts | I can stay aware of my diet performance. | -The system generates nutrition summary alerts based on user data. -Alerts reflect the user’s logged meals and nutrition intake. -Users can receive and view nutrition summary alerts clearly. |  | 2 |  |  |  | 4 | 20
PB23 | Receive Goal Achievement Notifications | User | Be notified when I reach | I can stay motivated and monitor | -The system detects when a user achieves a nutrition goal. -The system sends a goal achievement notification to the user. -Notifications correspond to the user’s actual progress. |  | 2 |  |  |  | 4 | 20
PB24 | Manage User Accounts | Admin | Manage user accounts | I can control access and maintain the system effectively. | -Admin can view user accounts. -Admin can update account status. -Admin can activate, deactivate, or manage accounts as needed. |  | 2 |  |  |  | 4 | 30
PB25 | Configure Access Rights | Admin | Configure permissions and system access rights | I can enforce proper system security and role management. | -Admin can assign roles and permissions. -Access rules are saved correctly. -Restricted features are only available to authorized roles. |  | 2 |  |  |  | 4 | 30
PB26 | Manage Food and Nutrition Data | Admin | Maintain food, recipe, and nutrition datasets | Users can receive accurate and updated nutrition information. | -Admin can add, edit, and delete food/nutrition records. -Updated data is reflected in the system -Invalid entries are prevented. |  | 2 |  |  |  | 4 | 30
PB27 | Monitor System Performance | Admin | Monitor analytics and system performance | I can ensure the platform runs reliably and efficiently. | -Admin can view system analytics. -Admin can monitor performance indicators. -Important system issues or abnormal behavior are visible. |  | 2 |  |  |  | 4 | 20
Note on M7: Fill in when a product backlog item has been assigned to a specific sprint. After a Sprint planning meeting is done.
Note on N7: Just rough numbers, 5,10,15,20 etc. Not 7, 13, 21 etc.

## Sprint 1 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
1.1 | PB01 | Design register screen UI | Nhi | Done | 6 | 6 | 0 | 6 | 0 | Day 1: 3; Day 2: 3
1.2 | PB01 | Implement registration form UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 3: 4; Day 4: 4
1.3 | PB01 | Implement register input validation | Nhi | Done | 4 | 4 | 0 | 4 | 0 | Day 5: 2; Day 6: 2
1.4 | PB01 | Build register API and account creation logic | Đạt | Done | 8 | 8 | 0 | 8 | 0 | Day 3: 4; Day 4: 4
1.5 | PB01 | Design user and authentication database schema | Khanh | Done | 4 | 4 | 0 | 4 | 0 | Day 1: 2; Day 2: 2
1.6 | PB02 | Implement login screen and form flow | Nhi | Done | 6 | 6 | 0 | 6 | 0 | Day 1: 3; Day 2: 3
1.7 | PB02 | Build login API and session handling | Đạt | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 4; Day 6: 4
1.8 | PB03 | Implement logout flow and session clear | Đạt | Done | 4 | 4 | 0 | 4 | 0 | Day 7: 2; Day 8: 2
1.9 | PB04 | Build forgot password request flow | Đạt | Done | 6 | 6 | 0 | 6 | 0 | Day 5: 3; Day 6: 3
1.10 | PB05 | Build reset password verification and update flow | Đạt | Done | 6 | 6 | 0 | 6 | 0 | Day 7: 3; Day 8: 3
1.11 | PB06 | Implement profile view and edit UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 7: 4; Day 8: 4
1.12 | PB06 | Create profile update endpoint and persistence | Đạt | Done | 6 | 6 | 0 | 6 | 0 | Day 7: 3; Day 8: 3
1.13 | PB07 | Implement personal diet goals setup UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 9: 4; Day 10: 4
1.14 | PB08 | Implement dashboard overview layout and widgets | Nhi | Done | 10 | 10 | 0 | 10 | 0 | Day 10: 4; Day 11: 3; Day 12: 3
1.15 | PB09 | Implement manual meal logging form | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 11: 4; Day 12: 4
1.16 | PB10 | Prepare food and nutrition data structure | Khanh | Done | 8 | 8 | 0 | 8 | 0 | Day 9: 4; Day 10: 4
1.17 | PB10 | Implement food search and selection UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 12: 4; Day 13: 4
1.18 | PB11 | Implement meal history list and detail view | Nhi | Done | 6 | 6 | 0 | 6 | 0 | Day 13: 2; Day 14: 2; Day 15: 2
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 122 | 122 | 0 | 122 | 0 | 8 | 8 | 8 | 8 | 9 | 9 | 12 | 12 | 8 | 12 | 7 | 11 | 6 | 2 | 2
|  |  |  | Burn down | [5 empty] | 114 | 106 | 98 | 90 | 81 | 72 | 60 | 48 | 40 | 28 | 21 | 10 | 4 | 2 | 0
|  |  |  | Burn up | [5 empty] | 8 | 16 | 24 | 32 | 41 | 50 | 62 | 74 | 82 | 94 | 101 | 112 | 118 | 120 | 122
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nhi |  | 6 | 6 | 4 | 4 | 2 | 2 | 4 | 4 | 4 | 8 | 7 | 11 | 6 | 2 | 2 | 72
[8 empty] | Huy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Đạt |  | 0 | 0 | 4 | 4 | 7 | 7 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 40
[8 empty] | Khanh |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 12
[8 empty] | Toàn |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Total team hours |  | 8 | 8 | 8 | 8 | 9 | 9 | 9 | 9 | 8 | 12 | 7 | 11 | 6 | 6 | 6 | 124
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 1 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 2 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
2.1 | PB12 | Design food scan UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 1: 4; Day 2: 4
2.2 | PB12 | Implement upload and camera input flow | Nhi | Done | 10 | 10 | 0 | 10 | 0 | Day 2: 4; Day 3: 3; Day 4: 3
2.3 | PB12 | Build image upload API endpoint | Đạt | Done | 10 | 10 | 0 | 10 | 0 | Day 3: 4; Day 4: 3; Day 5: 3
2.4 | PB12 | Prepare image storage mapping | Khanh | Done | 6 | 6 | 0 | 6 | 0 | Day 4: 2; Day 5: 2; Day 6: 2
2.5 | PB12 | Prepare food image dataset and preprocessing pipeline | Toàn | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 2; Day 6: 3; Day 7: 3
2.6 | PB12 | Integrate upload flow with recognition service | Đạt | Done | 8 | 8 | 0 | 8 | 0 | Day 6: 2; Day 7: 3; Day 8: 3
2.7 | PB13 | Implement analysis result UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 4; Day 6: 4
2.8 | PB13 | Build portion estimation service contract and logic | Đạt | Done | 12 | 12 | 0 | 12 | 0 | Day 8: 3; Day 9: 3; Day 10: 3; Day 11: 3
2.9 | PB13 | Prepare portion reference data and mapping | Khanh | Done | 6 | 6 | 0 | 6 | 0 | Day 9: 2; Day 10: 2; Day 11: 2
2.10 | PB13 | Train or tune portion estimation pipeline | Toàn | Done | 14 | 14 | 0 | 14 | 0 | Day 9: 3; Day 10: 3; Day 11: 4; Day 12: 4
2.11 | PB14 | Implement calorie and nutrition result display | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 8: 4; Day 9: 4
2.12 | PB14 | Build calorie and nutrition calculation API | Đạt | Done | 14 | 14 | 0 | 14 | 0 | Day 10: 4; Day 11: 5; Day 12: 5
2.13 | PB14 | Prepare nutrition calculation data model | Khanh | Done | 8 | 8 | 0 | 8 | 0 | Day 11: 3; Day 12: 3; Day 13: 2
2.14 | PB14 | Prepare food recognition inference pipeline | Toàn | Done | 20 | 20 | 0 | 20 | 0 | Day 12: 5; Day 13: 5; Day 14: 5; Day 15: 5
2.15 | PB15 | Implement save analysis result to meal log flow | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 13: 4; Day 14: 4
2.16 | PB15 | Build save analysis result endpoint and persistence | Đạt | Done | 12 | 12 | 0 | 12 | 0 | Day 13: 4; Day 14: 4; Day 15: 4
2.17 | PB16 | Implement low-confidence review and edit UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 14: 4; Day 15: 4
2.18 | PB16 | Build low-confidence handling and correction API | Đạt | Done | 12 | 12 | 0 | 12 | 0 | Day 14: 6; Day 15: 6
2.19 | PB16 | Store confidence score and correction history | Khanh | Done | 8 | 8 | 0 | 8 | 0 | Day 14: 4; Day 15: 4
2.20 | PB16 | Tune confidence scoring and post-processing rules | Toàn | Done | 12 | 12 | 0 | 12 | 0 | Day 14: 6; Day 15: 6
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 200 | 200 | 0 | 200 | 0 | 4 | 8 | 7 | 8 | 11 | 11 | 6 | 10 | 12 | 12 | 17 | 17 | 15 | 33 | 29
|  |  |  | Burn down | [5 empty] | 196 | 188 | 181 | 173 | 162 | 151 | 145 | 135 | 123 | 111 | 94 | 77 | 62 | 29 | 0
|  |  |  | Burn up | [5 empty] | 4 | 12 | 19 | 27 | 38 | 49 | 55 | 65 | 77 | 89 | 106 | 123 | 138 | 171 | 200
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nhi |  | 4 | 8 | 3 | 3 | 4 | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 8 | 4 | 50
[8 empty] | Huy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Đạt |  | 0 | 0 | 4 | 3 | 3 | 2 | 3 | 6 | 3 | 7 | 8 | 5 | 4 | 10 | 10 | 68
[8 empty] | Khanh |  | 0 | 0 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 2 | 5 | 3 | 2 | 4 | 4 | 28
[8 empty] | Toàn |  | 0 | 0 | 0 | 0 | 2 | 3 | 3 | 0 | 3 | 3 | 4 | 9 | 5 | 11 | 11 | 54
[8 empty] | Total team hours |  | 4 | 8 | 7 | 8 | 11 | 11 | 6 | 10 | 12 | 12 | 17 | 17 | 15 | 33 | 29 | 200
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 2 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Sprint 3 Backlog
Completed is ALWAYS the estimated (planned) number of hours. You NEVER put in the number of hours you worked.
[9 empty] | Compare your estimate with the actual number of hours you spent on the task, your effort - = Spent less time than estimated | Only update one time. When task is done. You update with the estimate hours, NOT the hours you actually worked to finish the task.
|  |  | Add Owner when task is set to Ongoing |  | Make new estimate when move from PB to SB |  | Remaining work to be done. | Total number of hours you spent on the task. Your effort
Sprint Backlog |  |  |  | Update status during sprint
Sprint Id | Backlog Id | Description | Owner | Status | Estimate (Hours) | Completed | Pending | Total effort | Effort vs. Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15
3.1 | PB17 | Design AI nutrition assistant UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 1: 4; Day 2: 4
3.2 | PB17 | Implement chat interface and message flow | Nhi | Done | 10 | 10 | 0 | 10 | 0 | Day 2: 4; Day 3: 3; Day 4: 3
3.3 | PB17 | Build chat query API and session handling | Đạt | Done | 12 | 12 | 0 | 12 | 0 | Day 3: 4; Day 4: 4; Day 5: 4
3.4 | PB17 | Integrate AI response flow with frontend | Đạt | Done | 10 | 10 | 0 | 10 | 0 | Day 5: 3; Day 6: 4; Day 7: 3
3.5 | PB18 | Design personalized recommendation UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 5: 4; Day 6: 4
3.6 | PB18 | Build recommendation generation API | Đạt | Done | 10 | 10 | 0 | 10 | 0 | Day 7: 3; Day 8: 4; Day 9: 3
3.7 | PB18 | Prepare user preference and recommendation data model | Khanh | Done | 6 | 6 | 0 | 6 | 0 | Day 8: 2; Day 9: 2; Day 10: 2
3.8 | PB18 | Tune personalized recommendation pipeline | Toàn | Done | 6 | 6 | 0 | 6 | 0 | Day 10: 2; Day 11: 2; Day 12: 2
3.9 | PB19 | Design meal plan and schedule UI | Nhi | Done | 10 | 10 | 0 | 10 | 0 | Day 8: 4; Day 9: 3; Day 10: 3
3.10 | PB19 | Build meal plan generation API | Đạt | Done | 14 | 14 | 0 | 14 | 0 | Day 10: 4; Day 11: 5; Day 12: 5
3.11 | PB19 | Prepare meal plan and nutrition rule dataset | Khanh | Done | 8 | 8 | 0 | 8 | 0 | Day 11: 4; Day 12: 4
3.12 | PB19 | Tune meal plan generation logic | Toàn | Done | 18 | 18 | 0 | 18 | 0 | Day 12: 6; Day 13: 6; Day 14: 6
3.13 | PB20 | Implement chat history list and detail UI | Nhi | Done | 8 | 8 | 0 | 8 | 0 | Day 13: 4; Day 14: 4
3.14 | PB20 | Build chat history storage and retrieval API | Đạt | Done | 12 | 12 | 0 | 12 | 0 | Day 13: 4; Day 14: 4; Day 15: 4
3.15 | PB20 | Prepare conversation and retrieval schema | Khanh | Done | 8 | 8 | 0 | 8 | 0 | Day 13: 4; Day 14: 4
3.16 | PB20 | Implement chat history search and filter UI | Nhi | Done | 12 | 12 | 0 | 12 | 0 | Day 14: 6; Day 15: 6
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
[6 empty] | 0 | 0 | 0 | 0
|  |  |  | Total | 160 | 160 | 0 | 160 | 0 | 4 | 8 | 7 | 7 | 11 | 8 | 6 | 10 | 8 | 11 | 11 | 17 | 18 | 24 | 10
|  |  |  | Burn down | [5 empty] | 156 | 148 | 141 | 134 | 123 | 115 | 109 | 99 | 91 | 80 | 69 | 52 | 34 | 10 | 0
|  |  |  | Burn up | [5 empty] | 4 | 12 | 19 | 26 | 37 | 45 | 51 | 61 | 69 | 80 | 91 | 108 | 126 | 150 | 160
[8 empty] | Worked hours/Day |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | Total hours
[8 empty] | Nhi |  | 4 | 8 | 3 | 3 | 4 | 4 | 0 | 4 | 3 | 3 | 0 | 0 | 4 | 10 | 6 | 56
[8 empty] | Huy |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[8 empty] | Đạt |  | 0 | 0 | 4 | 4 | 7 | 4 | 6 | 4 | 3 | 4 | 5 | 5 | 4 | 4 | 4 | 58
[8 empty] | Khanh |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 0 | 22
[8 empty] | Toàn |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 8 | 6 | 6 | 0 | 24
[8 empty] | Total team hours |  | 4 | 8 | 7 | 7 | 11 | 8 | 6 | 10 | 8 | 11 | 11 | 17 | 18 | 24 | 10 | 160
Above you can update actual worked hours every day for each team member to get a total number of hours in the sprint
Note on B7: ====== ID#AAAAeu_Dblw jan samuelsson (2022-08-23 14:14:25) 1st digit = Sprint number 2nd digit = Task number in this sprint
Note on C7: ====== ID#AAAAeu_Dbls jan samuelsson (2022-08-23 14:14:25) Reference to the product backlog item you have decided to do in this sprint. Usually a PB item is then divided into a number of Sprint tasks.

## Sprint 3 Reports
Reports & Dashboards
Burn down Chart | Burn up Chart

## Impediment
Impediments | [5 empty] | In charge of removing the impediment | Not started Ongoing Done
|  |  | Date | [5 empty] | Date
Id | Description | Raised By | Raised On | Sprint # | Impacted Backlog # | Owner | Status | Resolution | Resolved On

## Retrospective
In the retrospecitve meeting after each sprint you will identify/find many things to improve. That does not mean that you will do all the changes in the next sprint. Usually you do changes step by step. E.g. 1-3 changes in one sprint. Not more than that. So sometimes you find an improvement in one sprint and then in a much later sprint you will actually do the change.
Retrospective Log
Found in Sprint # | Impl. In Sprint # |  | Responsible for doing the improvement
Sprint # | Sprint # | Date | Owner | Start Doing (Improvement) | Continue Doing (What Went Well) | Stop Doing (Even better if) | Remarks

## References
References
External |  | Internal
Description | Link | Description | Link
Glossary & Terminology | https://www.scrumalliance.org/community/articles/2007/march/glossary-of-scrum-terms